## Project Tracker
Project Tracker
| Percent Over/Under to Flag | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2022-09-23 | 2022-11-22 | 210 | 59 | 2022-09-23 | 2022-11-27 | 1 | 300 | 0 | 64
Project 2 | Category 2 | Employee 4 | 2022-10-17 | 2022-11-17 | 400 | 30 | 2022-10-17 | 2022-11-20 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2022-08-19 | 2022-10-18 | 500 | 59 | 2022-08-19 | 2022-10-31 | 0 | 500 | 0 | 72
Project 4 | Category 2 | Employee 3 | 2022-08-29 | 2022-09-08 | 250 | 9 | 2022-08-29 | 2022-09-17 | 0 | 276 | 1 | 18
Project 5 | Category 3 | Employee 2 | 2022-08-29 | 2022-10-08 | 300 | 39 | 2022-08-29 | 2022-10-14 | 0 | 310 | 0 | 45
Project 6 | Category 4 | Employee 4 | 2022-09-28 | 2022-10-08 | 500 | 10 | 2022-09-28 | 2022-10-13 | 0 | 510 | 1 | 15
Project 7 | Category 5 | Employee 1 | 2022-10-14 | 2022-11-07 | 750 | 23 | 2022-10-14 | 2022-11-12 | 0 | 790 | 0 | 28
Project 8 | Category 2 | Employee 1 | 2022-10-19 | 2022-11-27 | 450 | 38 | 2022-10-13 | 2022-11-22 | 0 | 430 | 0 | 39
Project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS